## Sheet1
TEST REPORT: Journal Project
Test Name | Test features and UI for Student
Test Case Author | Luong Van Huy
Test Name | Luong Van Huy
Project Name | Journal Project (5mnews)
Date Tested | April 11th, 2021
Actor : Student
ID | Test Objective ID | Test Case Description | Test Case Procedure | Expected Result | Test Result | Defect note (optional) | status
Module 1-1 | test case for test plan 1-1: test feature log in for student | Test log in as student | 1. On the top right click on Sign In. 2. Fill in the valid student information into the form. 3. Click on "I'm not a robot" captcha. 4. Click on submit Button | 1. User is being redirect to student page 2. displayed test "Please enter your username!" if username not valid 3. displayed test "Please enter your password!" if username not valid 4. displayted text "The captcha field is required." if not click on "I'm not a robot" | pass |  | finished
Module 1-2 | test case for test plan 1-2: test feature log out for student | Test log out as student | 1. Click on the user icon on the top right. 2. On the drop down Click on Log out | User is being redirect to home page | pass |  | finished
Module 1-3 | test case for test plan 1-3: test feature view topic for student | test topic view as student. | 1. log in as student. | 1. Redirect to student page successfully. 2. topic that student have atleast one post displayed successfully in student page. | pass |  | finished
Module 1-4 | test case for test plan 1-4: test feature create post for student | test Create report for post | 1. Log in as student 2. Search topic available on the search bar 3. Select topic by clicking on it 4. Click on "Chọn Tệp" 5. Select files and Click "OK" 6. Click on Upload | 1. New uploaded files are displayed on Your Posts session. 2. If there no posts display "Không có tệp nào được chọn" | pass |  | finished
Sub Module 1-4 | test case special condition for module 1-4 | test Create report for post: Case - only post 1 .docs file for each topic | 1. Log in as student 2. Search topic available on the search bar 3. Select topic by clicking on it 4. Click on "Chọn Tệp" 5. Select files and Click "OK" 6. Click on Upload | 1. Notification on error or alert "only 1 docs file is allowed" | failed | 1. bug about this system can upload mutiple docx. | Skipped
Module 1-5 | test case for test plan 1-5: test feature update post for student | test Update report for post | 1. Log in as student 2. Select topic available in My Posts session in the student page 3. Clicked on Edit Posts 4. Select files and images. 5. Click Save. | 1. New uploaded files are displayed on Your Posts session. 2. On the Edit post modal if there no files display "Không có tệp nào được chọn" | pass |  | finished
Module 1-6 | test case for test plan 1-6: test feature delete post for student | test Delete report for post | 1. Log in as student 2. Select topic available in the student page 3. Click on "Remove Posts" 4. Click Confirm. | 1. files and images are removed from Topic. 2. The Topic also removed from My Posts session | failed | 1. if existed at least 1 comment so the post will not be removed from My Post session | Debugging
Module 1-7 | test case for test plan 1-7: test feature view posts for student | test view posts | 1. Log in as student 2. Select topic available in the student page | 1. Redirect to submit posts page. 2. Submitted files displayed successfully. | pass |  | finished
Module 1-8 | test case for test plan 1-9: test feature support for student | test support feature | 1. Click support on the navbar. 2. Fill in required information. 3. Click Submit | 1. Redirect back to home page. 2. notification on sending request successfully. | failed | 1) Policy 2) cannot find support feature for student | Skipped
Module 1-9 | test case for test plan 1-9: test feature comment for student on Submit Posts page | test comment features | 1. Log in as student 2. Select topic available in My Posts in the student page 3. scroll down as the comment session, type in comment. 4. click submit | 1. new comment displayed successfully | pass |  | finished
Module 1-10 | test case for test plan 1-10: test feature delete comment for student on Submit Posts page | delete comment features | 1. Log in as student 2. Select topic available in the student page 3. scroll down as the comment session, type in comment. 4. select comment and click delete 5. click confirm | 1. selected comment is remove from the comment session | failed | 1) after click submit delete, selected comment is still there. 2) the comment is just disappear after refresh(f5) | Debugging
Module 1-11 | test case for test plan 1-12: view profile for student | Test profile as student | 1. log in as student 2. Click the icon user on the top right of the page. 3. On the dropdown select profile. | 1. User is redirected to student profile page. | pass | 1. profile not shown when clicking on profile (fixed). | finished
Module 1-12 | test case for test plan 1-12: edit profile for student | edit profile | 1. On profile page click on pencil icon located center of the profile images. 2. Fill in new information 3. Click Update | 1. User is redirected to edit profile page. 2. After click update redirect to profile page. 3. Displayed editted information in the profile page successfully. | pass |  | finished
Test Name | Test features and UI for Coordinator
Test Case Author | Luong Van Huy
Test Name | Luong Van Huy
Project Name | Journal Project (5mnews)
Date Tested | April 11th, 2021
Actor: Marketing Coordinator
ID | Test Objective ID | Test Case Description | Test Case Procedure | Expected Result | Test Result | Defect note (optional) | status
Module 2-1 | test case for test plan 2-1: test feature log in for coordinator | Test log in as marketing coordinator | 1. On the top right click on Sign In. 2. Fill in the valid marketing coordinator information into the form. 3. Click on "I'm not a robot" captcha. 4. Click on submit Button | 1. User is being redirect to marketing coordinator page 2. displayed test "Please enter your username!" if username not valid 3. displayed test "Please enter your password!" if username not valid 4. displayted text "The captcha field is required." if not click on "I'm not a robot" | pass | Need fixed on the text "Manage Account" to "Manage Topic" | finished
Module 2-2 | test case for test plan 2-2: test feature log out for coordinator | Test log out as marketing coordinator | 1. Click on the user icon on the top right. 2. On the drop down Click on Log out | User is being redirect to home page | pass |  | finished
Module 2-3 | test case for test plan 2-3: test feature create topic for coordinator | test create topic | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, click on create button on the top left of the page 4. fill in the input and import images(optional). 5) select closureDate . 6) click on Create | 1. redirect back to the manage topic page. 2. new Topic and image are displayed in manage topic page | pass |  | finished
Module 2-4 | test case for test plan 2-4: test feature update topic for coordinator | test update topic | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic and click on pencil icon of that posts 5. edit data and import images(optional). 6. edit closureDate . 7. click on Save | 1. redirect back to the home page. 2. notification on update successfully 3. new information is added to database. | failed | 1. when clicked save, it create new one instead of update the old one. | Skipped
Module 2-5 | test case for test plan 2-5: test feature delete topic for coordinator | test delete topic | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic by check on the checkbox 5. click delete button on the top left of the page. 7. click on Confirm | 1. The selected topic is remove from the manage topic table 2. if no topics selected then redirect to the coordinator page. | failed | 1. Some posts cannot be delete. | Debugging
Module 2-6 | test case for test plan 2-6: test feature view post for coordinator | test view post | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic and click on "View List Post" | 1. User is redirected to post page. 2. All posts displayed successfully. | pass |  | finished
Module 2-7 | test case for test plan 2-7: test feature delete post for coordinator | test delete post | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic and click on "View List Post" 5. select post by click on garbage bin icon | 1. notification on delete successfully. 2. remove deleted post from database. | failed | cannot find the way to delete post | pending
Module 2-8 | test case for test plan 2-8: test change posts status for coordinator | test change post status | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic and click on "View List Post" 5. select post and click on "View Details" 6. Scroll down to "Cencorship session" 7. select status "Qualified" or "Unstatisfactory" 8. Click submit | 1. new status is updated successfully p/s: not clear outcome of this flow | pass |  | finished
Module 2-9 | test case for test plan 2-8: test email feature for coordinator | check email feature for marketing coordinator | 1. Use Student account to create a post 2. Check email of marketing coordinator | 1. Email have sent successfully . 2. Email existed in the marketing coordinator email: huyluongvan0109@gmail.com | pass | 1. At first this feature can be checked because we not defined specific flow for it. 2. After defininng we decide to get 1 mail to represent for coordinator | finished
Module 2-10 |  | test support feature as marketing coordinator | 1. Click support on the navbar 2. Select support ticket 3. Comment in. 4. Click on submit | 1. Show all the support tickets. 2. update new comment for selected post successfully. |  |  | Skipped
Module 2-11 |  | test select post for public | 1. Click post on the navbar. 2. Select post and clicked on public. | 1. Notification on select successfully. 2. The selected post is displayed in the public post. |  |  | Skipped
Module 2-12 | test case for test plan 2-12: test comment feature for coordinator | test comment features | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic and click on "View List Post" 5. select post and click on "View Details" 6. Scroll down to "Comment session" and type in comment 8. Click submit | 1. new comment displayed successfully. | pass |  | finished
Module 2-13 | test case for test plan 2-13: test delete comment feature for coordinator | delete comment features | 1. log in as coordinator. 2. on the coordinator page, click on manage topic. 3. on the manage topic page, 4. select topic and click on "View List Post" 5. select post and click on "View Details" 6. Scroll down to "Comment session" and select comment by click on delete icon 7. click submit. | 1. selected comment is remove from the comment session. 2. delete icon only displayed for coordinator comment | failed | 1) after click submit delete, selected comment is still there. 2) the comment is just disappear after refresh(f5) | pending
Module 2-14 | test case for test plan 2-14: view profile for coordinator | Test profile as admin | 1. log in as coordinator 2. Click the icon user on the top right of the page. 3. On the dropdown select profile. | 1. User is redirected to coordinator profile page. | pass | 1. profile not shown when clicking on profile (fixed). | finished
Module 2-15 | test case for test plan 2-15: edit profile for coordinator | edit profile | 1. On profile page click on pencil icon located center of the profile images. 2. Fill in new information 3. Click Update | 1. User is redirected to edit profile page. 2. After click update redirect to profile page. 3. Displayed editted information in the profile page successfully. | pass |  | finished
Test Name | Test features and UI for Manager
Test Case Author | Luong Van Huy
Test Name | Luong Van Huy
Project Name | Journal Project (5mnews)
Date Tested | April 11th, 2021
Actor: Marketing Manager
ID | Test Objective ID | Test Case Description | Test Case Procedure | Expected Result | Test Result | Defect note (optional) | status
Module 3-1 | test case for test plan 3-1: test feature log in for manager | Test log in as Marketing Manager | 1. On the top right click on Sign In. 2. Fill in the valid Marketing Manager coordinator information into the form. 3. Click on "I'm not a robot" captcha. 4. Click on submit Button | 1. User is being redirected to Marketing Manager page 2. displayed test "Please enter your username!" if username not valid 3. displayed test "Please enter your password!" if username not valid 4. displayted text "The captcha field is required." if not click on "I'm not a robot" | pass |  | finished
Module 3-2 | test case for test plan 3-2: test feature log out for manager | Test log out as Marketing Manager | 1. Click on the user icon on the top right. 2. On the drop down Click on Log out | User is being redirect to home page | pass |  | finished
Module 3-3 | test case for test plan 3-3: test feature view topic for manager | test view topic | 1. log in as manager. 2. select the faculty by clicking on it. | 1. User is redirected to list topic page. 2. All topic of selected faculty is successfully displayed | pass |  | finished
Module 3-4 | test case for test plan 3-4: test feature view post by topic for manager | test view post by topic | 1. log in as manager. 2. select the faculty by clicking on it. 3. select topic by clicking on it | 1. All the posts satisfied selected topic is displayed. | pass |  | finished
Module 3-5 | test case for test plan 3-5: test feature view post by topic for manager (empty case) | test view post by topic (empty case) | 1. log in as manager. 2. select the faculty by clicking on it. 3. select topic by clicking on it | 1. displayed text "No topic was created" | pass |  | finished
Module 3-6 | test case for test plan 3-6: test feature search post by name for manager | test search post by name | 1. log in as manager. 2. select the faculty by clicking on it. 3. in search input name of the post. | 1. All the result that meet the input is displayed to the screen | pass |  | finished
Module 3-7 | test case for test plan 3-7: test feature search post by name for manager (empty case) | test search post by name(empty case) | 1. log in as manager. 2. select the faculty by clicking on it. 3. in search input name of the post. | 2. display text "No matching records found" | pass |  | finished
Module 3-8 | test case for test plan 3-8: test feature zip for manager (empty case) | test download zip post as marketing manager | 1. log in as manager. 2. select the faculty by clicking on it. 3. select post by check it in the checkbox input 4. click download on the top left of the page | 1. all selected post is zipped and download properly | pass |  | finished
Module 3-9 | test case for test plan 3-9: view profile for manager | Test profile as admin | 1. log in as manager 2. Click the icon user on the top right of the page. 3. On the dropdown select profile. | 1. User is redirected to manager profile page. | pass | 1. profile not shown when clicking on profile (fixed). | finished
Module 3-10 | test case for test plan 3-9: edit profile for manager | edit profile | 1. On profile page click on pencil icon located center of the profile images. 2. Fill in new information 3. Click Update | 1. User is redirected to edit profile page. 2. After click update redirect to profile page. 3. Displayed editted information in the profile page successfully. | pass |  | finished
Test Name | Test features and UI for Manager
Test Case Author | Luong Van Huy
Test Name | Luong Van Huy
Project Name | Journal Project (5mnews)
Date Tested | April 11th, 2021
Actor: Admin
ID | Test Objective ID | Test Case Description | Test Case Procedure | Expected Result | Test Result | Defect note (optional) | status
Module 4-1 | test case for test plan 4-1: test feature log in for admin | Test log in as admin | 1. On the top right click on Sign In. 2. Fill in the valid Admin coordinator information into the form. 3. Click on "I'm not a robot" captcha. 4. Click on submit Button | 1. User is being redirected to admin page successfully 2. displayed test "Please enter your username!" if username not valid 3. displayed test "Please enter your password!" if username not valid 4. displayted text "The captcha field is required." if not click on "I'm not a robot" | pass |  | finished
Module 4-2 | test case for test plan 4-2: test feature log out for admin | Test log out as admin | 1. Click on the user icon on the top right. 2. On the drop down Click on Log out | User is being redirect to home page | pass |  | finished
Module 4-3 | test case for test plan 4-3: test feature profile for admin | Test profile as admin | 1. log in as admin 2. Click the icon user on the top right of the page. 3. On the dropdown select profile. | 1. User is redirected to admin profile page. | pass | 1. profile not shown when clicking on profile (fixed). | finished
Submodule 4-3 |  | edit profile | 1. On profile page click on pencil icon located center of the profile images. 2. Fill in new information 3. Click Update | 1. User is redirected to edit profile page. 2. After click update redirect to profile page. 3. Displayed editted information in the profile page successfully. | pass |  | finished
Module 4-4 | test case for test plan 4-4: test feature forget password for admin | Test forget password as admin | 1. On the log in form click on forget password 2. Fill in the required information with valid information 3. Click on submit | notification on password successfully changed |  | Don’t know how to test this flow | Skipped
Module 4-5 | test case for test plan 4-5: test feature change password for admin | test change password feature as admin | 1. Click on the profile on the navbar. 2. Click on change password in the profile page. 3. fill in valid information. 4. click on submit. | notification on password successfully changed |  | Don’t know how to test this flow | Skipped
Module 4-6 | test case for test plan 4-6: test feature view account for admin | test view account of admin | 1. Log in as admin 2. Click on manage accounts. | 1. All the accounts have displayed successfully | pass |  | finished
Submodule 4-6 |  | search account of admin | 1. On manage account page, type in the name of the acccount in the search bar. | 1. All the account meet the search input displayed successfully | pass |  | finished
Module 4-7 | test case for test plan 4-7: test feature create account for admin | test create account of admin | 1. Log in as admin 2. Click on manage accounts. 3. Click on create button. 4. Fill in valid information. 5. click on create | 1. New account is displayed in the account table. 2. notification on create successfully 3. redirected to account table. | pass |  | finished
Module 4-8 | test case for test plan 4-8: test feature Update account for admin | test update account of admin | 1. Log in as admin 2. Click on manage accounts. 3. select account by click on it pencil icon 4. Fill in valid information. 5. click on updated | 1 .redirected to account table. 2. editted account is displayed in the account table. | pass | cannot see the updated account | finished
Module 4-9 | test case for test plan 4-9: test feature Delete account for admin | test delete account of admin | 1. Log in as admin 2. Click on manage accounts. 3. Select account by clicking on checkbox input. 4. click in delete button on the top left of the menu. 5. click on ''OK" | 1. Selected account is removed from the account table. | pass |  | finished
Module 4-10 | test case for test plan 4-10: test feature view specific account | test feature view specific account | 1. Log in as admin 2. Click on manage accounts. 3. Select account by clicking on factorial icon | 1. redirected to details account page 2. displayed selected account successfully | pass |  | finished
Module 4-11 | test case for test plan 4-1: test feature log in for admin | test view academic year(Empty case) | 1. On the side nav click on Academic Year or click on manage academic year | 1. displayed text "No data available in table" | pass |  | finished
Module 4-12 | test case for test plan 4-12: test feature view academic year for admin | test view academic year | 1. On the side nav click on Academic Year or click on manage academic year | 1. All the academic year displayed successfully | pass |  | finished
Sub module 4-12 |  | test view specific academic year | 1. On the side nav click on Academic Year or click on manage academic year. 2. choose academic year by click on it factorial icon | 1. redirected to details academic year page 2. displayed selected account successfully | pass |  | finished
Module 4-13 | test case for test plan 4-13: test feature create academic year for admin | test create academic year | 1. On the side nav click on Academic Year 2. Click on create. 3. fill in the required information 4. Click on create | 1. the new Academic year is updated and displayed in the academic year page | pass | the Date format is incorrect | finished
Module 4-14 | test case for test plan 4-14: test feature delete academic year | test delete academic year | 1. On the side nav click on Academic Year 2. select academic year by clicking on it checkbox 3. click delete button on the top left of the page 4. Click 'OK' | 1. the selected academic year is remove from the table | pass | cannot create so that cannot test delete | finished
Module 4-15 | test case for test plan 4-15: test feature update academic year | test update academic year | 1. On the side nav click on Academic Year 2. select academic year by clicking on it pencil icon 3.Fill in the required new information 4. Click 'Update' | 1. redirected academic year page 2. new information or edit information is displayed successfully | failed | pencil icon redirected user to edit faculty | pending
Module 4-16 | test case for test plan 4-16: test feature statistical analysis for admin | test statistical analysis | 1. log in as admin 2. click on statical report 3. Click go | 1. redirected to statistical page. 2. all statistical chart is displayed successfully | pass |  | finished
Module 4-17 | test case for test plan 4-17: test feature view topic for admin | test view topic as admin | 1. On the side nav click on topic or manage topics on the dashboard | 1. All the topic meet the successfully displayed. | pass |  | finished
Sub Module 4-17 |  | test view specific topic as admin | 1. Log in as admin 2. Click on manage topic. 3. Select topic by clicking on factorial icon | 1. redirected to details topic page 2. displayed selected topic successfully | pass |  | finished
Module 4-18 | test case for test plan 4-1: test feature view post for admin | test view post | 1. On the side nav click on post or manage post on the dashboard | 1. Redirected to manage post page 2. All the post displayed to the screen successfully | pass |  | finished
Module 4-19 | test case for test plan 4-19: test feature create topic for admin | test create topic of admin | 1. On the side nav click on topic or manage topics on the dashboard 2. on the topic page click create 3. fill in information 4. Click create | 1. new topic is displayed in the topic table | pass |  | finished
Module 4-20 | test case for test plan 4-20: test feature update topic for admin | test update topic of admin | 1. On the side nav click on topic or manage topics on the dashboard 2. on the topic page select topic by clicking on it pencil icon 3. edit in information 4. Click Update | 1. editted topic is displayed in the topic table | failed | error format date is not valid | pending
Module 4-21 | test case for test plan 4-21: test feature delete topic for admin | test delete topic of admin | 1. On the side nav click on topic or manage topics on the dashboard 2. on the topic page select topic by clicking on it checkbox 3. click delete in the top left of the page 4. Click confirm | 1. selected topic is removed in the topic table | pass |  | finished
Module 4-22 | test case for test plan 4-22: test feature view posts for admin | test view post of admin | 1. On the side nav click on post or click manage post in the admin page | 1. User is redirected to post page. 2. All the post is display successully | pass |  | finished
Module 4-23 | test case for test plan 4-23: test feature delete post for admin | test delete post of admin | 1. On the side nav click on posts or manage posts on the dashboard 2. on the posts page select posts by clicking on it checkbox 3. click delete in the top left of the page 4. Click confirm | 1. selected posts is removed in the topic table | pass |  | finished